## Master
Weeks | Topics | Important Milestones | Deliverables
Week 1 | Onboarding and Basic Research skills | Onboarding and Project Assignment + Stakeholder Meetings | A work plan + Start a draft of literature review + A refined research question
Week 2 | Basic Programming skills | Literature Review + Complete DATACAMP + Stakeholder Meetings + Start R-Shiny App | A completed draft of literature review + Complete DATACAMP + A simple R-Shiny App + Start Github + A stakeholder meeting summary
Week 3 | Data skills - multimodality | Collect data + Add to R-Shiny App | Completed dataset + A more complicated R-Shiny App product
Week 4 | Data Exploratory skills | Explore data patterns and start draft of data and descriptive statistics | A more advanced R Shiny App product + A draft of data section and descriptive statistics
Week 5 | Data Modeling skills | Conduct modeling analysis | A draft of models and preliminary results
Week 6 | Advanced skills and topics | Conduct modeling analysis + Midterm Check In with Stakeholders | A revised draft of results + Presenting to stakeholders
Week 7 | Project Work | Wrap up datawork, start Kohl Insights & poster | A preliminary poster + A revised Shiny App + Started a draft of Kohl Insights
Week 8 | Project Work | Deploy Version 1 of Shiny App + Abstract submission to symposium + Kohl Insights | A close-to-finished poster, R-Shiny, Kohl Insights + Abstract for symposium to be submitted by July 15
Week 9 | Project Work | Finalize poster, Kohl Insights, Shiny APP | A completed poster, R-Shiny, Kohl Insights
Week 10 | Finalize Project | Presentaions: Summer VT Undergraduate Research Symposium + stakeholders | Publish R-Shiny App and Kohl Insights, Finalize Github repo, Presentations to stakeholders and at Symposium
To plan:
Schedule Training with Library
Schedule Stakeholder Meetings
Schedule Workshops
Reserve Rooms
Schedule with Normand for May 26 at 9 am for photos
Schedule Faculty Advisors Office Hours and Meeting Times
Schedule Graduate Fellow Office hours
Schedule faculty leads office hours

## Personnel
Key Personnel
Title | Name | Contact | Office Location | Office Hours
DSPG Director | Dr. Le Wang |  | Hutch 321B
Faculty Leads-Program Management
Dr. Michael Cary
Dr. Yujuan Gao
Curriculum Lead | Dr. Chunbei Wang |  | Hutch 321A
Graduate Fellows
| Xiaoyi Zhao - lead | xiaoyiz@vt.edu | Kohl Centre Hutch 320
| Yuanyuan Wen | yuanyuanw@vt.edu | Kohl Centre Hutch 320
| Pragati Dahal | pdahal@vt.edu | Kohl Centre Hutch 320
| Angana Chatterjee | anganac@vt.edu | Kohl Centre Hutch 320
| Suyog Gautam | suyoggtm@vt.edu | Kohl Centre Hutch 320
| Xiaofan Zhu | zxiaofan@vt.edu | Kohl Centre Hutch 320
Faculty Advisors
Dr. Isabel Bradburn
Dr. Huaiyang Zhong
Dr. Michael Cary
Dr. Yujuan Gao
Dr. Le Wang
Team | Undergrad Interns + Grad Fellows + Faculty advisors
Project Team Assignment
| Project 1 xxx | Project 2 xxx | Project 3 xxx | Project 4 xxx | Project 5 xxx
Work Space | Hutch 311 | Hutch 221 | Hutch 324 | Hutch 322 | Hutch 319B
Grad Fellows | xx | xx | xx | xx | xx
| xx | xx | xx | xx | xx
Faculty Advisors | Dr. Le Wang | Dr. Le Wang | Dr. Le Wang | Dr. Le Wang | Dr. Le Wang
| xx | xx | xx | xx | xx
Undergrad Interns | xx | xx | xx | xx | xx
| xx | xx | xx | xx | xx

## Week 1
Week 1: Onboarding, Project Assignment, Introduction to Research
Date | Event/Activities | Time | Location | Responsible Parties
Sun, May 24 | Move into Dorm
| Check in at New Hall West for dorm assignment | 12:30 |  | Dr. Michael Cary will send information
Mon, May 25 | Memorial day - no activities
Tue, May 26 | Onboarding and Introduction
Morning:
| ONBOARDING: -Check that the participation agrement was signed, -CITI training was complete. -Eduroam access, -Network Access in building, -PRE-SURVEY is complete, -Sign contract for pics, -Pre-Survey -Q&A | 8:00 AM - 9:00 AM |  | Drs. Michael Cary and Yujuan Gao
| COFFEE & DONUTS, Welcome Interns - introduce everyone -Normand take photos | 9:00 AM - 10:00 AM |  | All Teams + Normand
| Faculty Present Projects to the Interns | 10:00 AM - 12:00 PM |  | Drs. Le Wang, Yujuan Gao, and Michael Cary
Afternoon:
| Interns meet with project teams, go over expectations and faculty office hours | 1:00 PM - 3:00 PM |  | Faculty Advisors and Grad Fellows
| Interns work on setting up software and team communication - TEAMS, GIT, Downloading Software - R, R Studio, R markdown, Data Camp - GIT Ruben Bramasco Video | 3:00 PM - 5:00 PM |  | Dr. Michael Cary, Dr. Yujuan Gao, and Grad Fellows
Wed, May 27 | Orientation with University - Full Day Event
Thu, May 28 | Introduction to Research
Morning:
| Workshop - Introduction to Research | 9:00 AM - 10:20 AM | Kohl Centre Hutch 320 | Dr. Le Wang
| Workshop - How to work with stakeholders | 10:30 AM - 12:00 PM | Kohl Centre Hutch 320 | Dr. Eric Kaufman
Afternoon:
| Interns work on project - collect literature - discuss research question for the project - prepare questions for the stakeholders | 1:00 PM - 5:00 PM |  | Grad Fellows available for questions
Fri, May 29 | Introduction to Literature Review and Meeting Stakeholders
Morning:
| Workshop - How to conduct literature review | 8:30 AM - 10:00 AM | Kohl Centre Hutch 320 | Dr. Yujuan Gao
| Interns work on project - search, read, and summarize literature | 10:00 AM - 12:00 PM
| Interns meet with Stakeholder - potential slots (schedule 1/2 hour meetings) | 10:00 AM - 12:00 PM |  | Project Team and Stakeholder
| Interns meet with Stakeholder - USDA Rural Health Project | 11:00 AM - 11:30 AM | https://virginiatech.zoom.us/j/84063019122?pwd=nDBLHfJMG1E2k1OKmQUnRcDPhmHrnJ.1 | Project Team and Dr. Paula Masters (VP Chief Health Disparities Officer at Ballad Health)
Afternoon:
| Interns work on project - start a draft of literature review - develop a work plan | 1:00 PM - 5:00 PM |  | Grad Fellows available for questions
| Interns meet with Stakeholder - potential slots (schedule 1/2 hour meetings) | 1:00 PM - 5:00 PM |  | Project Team and Stakeholder
VCE-AI Project Stakeholder Meeting (prefers after 2:00; can meet from 10:00-2:00)
Cals Walks Project Stakeholder Meeting (12:00-3:00)
Week 1 Deliverables: | Start a draft of literature review
A more refined research question based on literature review
A work plan

## Week 2
Week 2: Basic Programming Training and Work on Projects
Date | Event/Activities | Time | Location | Responsible Parties
Mon, Jun 1 | R Basics & Training
Morning:
| Office hour | 8:00 AM - 9:00 AM |  | Dr. Michael Cary (and/or Dr. Yujuan Gao)
| Workshop - R Basics & Training Section 1 | 9:00 AM - 12:00 PM | Library 124 Athenaeum | Nathaniel/Jesse
Afternoon:
| Interns work on DATACAMP and practice R with Project Data | 1:00 PM - 3:30 PM |  | Grad Fellows available for questions
| Interns work on Project - Read literature and refine research question | 3:30 PM - 5:00 PM |  | Grad Fellows available for questions
Tue, Jun 2 | R Basics & Training
Morning:
| Office hour | 8:00 AM - 9:00 AM |  | Dr. Michael Cary (and/or Dr. Yujuan Gao)
| Workshop - R Basics & Training Section 2 | 9:00 AM - 12:00 PM | Library 124 Athenaeum | Nathaniel/Jesse
Afternoon:
| Interns work on DATACAMP and practice R with Project Data | 1:00 PM - 3:30 PM |  | Grad Fellows available for questions
| Interns work on Project - Draft literature review | 3:30 PM - 5:00 PM |  | Grad Fellows available for questions
Wed, Jun 3 | GIT Basics & Training
Morning:
| Office hour | 8:00 AM - 9:00 AM |  | Dr. Michael Cary (and/or Dr. Yujuan Gao)
| Workshop - GIT Basics & Training | 9:00 AM - 12:00 PM | Library 124 Athenaeum | Nathaniel/Jesse
Afternoon:
| Interns work on DATACAMP and practice Git and Github: Branching, Pull Requests | 1:00 PM - 3:30 PM |  | Grad Fellows available for questions
| Interns work on Project - Draft literature review | 3:30 PM - 5:00 PM |  | Grad Fellows available for questions
Thu, Jun 4 | R Shiny and Markdown Basic Training
Morning:
| Office hour | 8:00 AM - 9:00 AM |  | Dr. Michael Cary (and/or Dr. Yujuan Gao)
| Workshop - R Shiny and R Markdown Basics & Training | 9:00 AM - 12:00 PM | Library 124 Athenaeum | Nathaniel/Jesse
Afternoon:
| Interns work on DATACAMP and practice R Shiny and R Markdown | 1:00 PM - 3:30 PM |  | Grad Fellows available for questions
| Interns work on Project - Build a simple version of R Shiny app for project | 3:30 PM - 5:00 PM |  | Grad Fellows available for questions
Fri, Jun 5 | Organization and Template
Morning:
| Office hour | 8:00 AM - 9:00 AM |  | Dr. Michael Cary (and/or Dr. Yujuan Gao)
| Workshop - Coding Organization & Standard Template | 9:00 AM - 10:00 AM | Kohl Centre Hutch 320 | Xiaoyi Zhao
| Workshop - Organizing and Documenting Data Availability | 10:00 AM - 11:00 AM | Kohl Centre Hutch 320 | Pragati Dahal
| Interns implement organization and documentation template | 11:00 AM - 12:00 PM |  | Grad Fellows
| Interns meet with Stakeholder - potential slots (schedule 1/2 hour meetings) | 11:00 AM - 12:00 PM |  | Project Team and Stakeholder
Afternoon:
| Interns work on Project - Build a simple version of R Shiny app for project | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Interns meet with Stakeholder - potential slots (schedule 1/2 hour meetings) | 1:00 PM - 4:00 PM |  | Project Team and Stakeholder
| Push progress to GIT, make sure to follow Template, reflect | 4:00 PM - 5:00 PM |  | Grad Fellows
Week 2 Deliverables: | A completed draft of literature review
A simple version of R Shiny app product
Completion of DATACAMP
A Github
A Stakeholder meeting summary

## Week 3
Week 3: Data Skills - Multimodality
Date | Event/Activities | Time | Location | Responsible Parties
Mon, Jun 8 | AI & Ethics Workship and Work on data
Morning:
| Grad Fellows and Interns meet with faculty leads to plan for the week - Faculty leads talk about big picture and goals - Grad Fellows meet with individual groups to assign tasks | 8:00 AM - 9:00 AM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Workshop - AI & Ethics | 10:00 AM - 12:00 PM |  | Drs. Rockwell Clancy and Elena Serrano
Afternoon:
| Interns work on Project - Work on data collection/cleaning and develop R-Shiny | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Tue, Jun 9 | Structured and Large Dataset and Work on project
Morning:
| Workshop - Structured and Large Dataset | 9:00 AM - 11:00 AM | Kohl Centre Hutch 320 | Xiaoyi Zhao
Interns work on Project - Work on data collection/cleaning and develop R-Shiny
Afternoon:
| Interns work on Project - Work on data collection/cleaning and develop R-Shiny | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Wed, Jun 10 | Transportation and Health Access Data
Morning:
| Workshop - Transportation and Health Access Data | 9:00 AM - 11:00 AM | Kohl Centre Hutch 320 | Junghwan?
Afternoon:
| Interns work on Project - Work on data collection/cleaning and develop R-Shiny | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Thu, Jun 11 | Remote Sensing Data
Morning:
| Workshop - Remote Sensing Data | 9:00 AM - 11:00 AM | Kohl Centre Hutch 320 | Shao Yang's Student?
Afternoon:
| Interns work on Project - Work on data collection/cleaning and develop R-Shiny | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Fri, Jun 12 | Text data (optional)
Morning:
| Prepare for progress report | 8:00 AM - 10:00 AM |  | Grad Fellows
| Progress Report (10-15 minute presentation + 5-10 minutes Q&A) | 10:00 AM - 12:00 PM | Hutch 302 | All Teams + Faculty
Afternoon:
| Interns work on Project - Work on data collection/clearning and develop R-Shiny - Incorporate feedback | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Week 3 Deliverables: | Complete data collection
A more complicated R shiny app product
A progress report

## Week 4
Week 4: Data Exploratory Skills
Date | Event/Activities | Time | Location | Responsible Parties
Mon, Jun 15 | Reduction Technique
Morning:
| Grad Fellows and Interns meet with faculty leads to plan for the week - Faculty leads talk about big picture and goals - Grad Fellows meet with individual groups to assign tasks | 8:00 AM - 9:00 AM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Workshop - Reduction technique: index building | 9:00 AM - 11:30 AM | Kohl Centre Hutch 320 | Dr. Huaiyang Zhong or Yang Cheng ??
Afternoon:
| Interns work on Project - Work on data exploratory analysis - Draft data section and communicate data patterns | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Tue, Jun 16 | Advanced Data Visualization and Exploratory Analysis
Morning:
| Workshop - Advanced Data Visualization & Exploratory Analysis | 9:00 AM - 12:00 PM | Kohl Centre Hutch 320 | Yuanyuan Wen
Afternoon:
| Interns work on Project - Work on data exploratory analysis - Draft data section and communicate data patterns | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Wed, Jun 17 | Advanced R Shiny
Morning:
| Workshop - Advanced R Shiny | 9:00 AM - 10:30 AM | Kohl Centre Hutch 320 | Yuanyuan Wen
Interns work on Project - Work on data exploratory analysis and develop advanced R-Shiny - Draft data section and communicate data patterns
Afternoon:
| Interns work on Project - Work on data exploratory analysis and develop advanced R-Shiny - Draft data section and communicate data patterns | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Thu, Jun 18 | Project Work
Morning:
| Prepare for progress report | 8:00 AM - 10:00 AM |  | Grad Fellows
| Progress Report (10-15 minute presentation + 5-10 minutes Q&A) | 10:00 AM - 12:00 PM | Hutch 302 | All Teams
Afternoon:
| Interns work on Project - Work on data and develop advanced R-Shiny - Incorporate feedback | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Fri, Jun 19 | Juneteenth holiday - no activities
Week 4 Deliverables: | A more advanced R Shiny App product
A draft of data section and descriptive statistics
A progress report

## Week 5
Week 5: Data Modeling Skills
Date | Event/Activities | Time | Location | Responsible Parties
Mon, Jun 22 | Introduction to Statistics
Morning:
| Grad Fellows and Interns meet with faculty leads to plan for the week - Faculty leads talk about big picture and goals - Grad Fellows meet with individual groups to assign tasks | 8:00 AM - 9:00 AM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Workshop - Introduction to Statistics - Hypothesis testing - Common statistical models: regression and classification | 9:00 AM - 12:00 PM | Kohl Centre Hutch 320 | Dr. Yujuan Gao
Afternoon:
| Interns work on Project - Work on basic statistical modeling and hypothesis testing | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Tue, Jun 23 | Causal Inference I
Morning:
| Interns work on Project - start a draft of models and hypotheses | 8:00 AM - 10:00 AM
| Workshop - Causal Inference Philosophy and Introduction | 10:00 AM - 12:00 PM | Kohl Centre Hutch 320 | Dr. Le Wang
Afternoon:
| Workshop - Causal Inference Methods and Implementations - RCT, DID, Synthetic Control | 1:00 PM - 3:00 PM | Kohl Centre Hutch 320 | Dr. Yujuan Gao
| Interns Work on Project - Work on advanced models and update draft - Interpret and draft results | 3:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Wed, Jun 24 | Causal Inference II
Morning:
| Workshop - Causal Inference Methods and Implementations - Propensity Score, IV, RDD | 9:00 AM - 11:00 AM | Kohl Centre Hutch 320 | Pragati Dahal
Interns Work on Project - Work on advanced models and update draft - Interpret and draft results
Afternoon:
| Interns Work on Project - Work on advanced models and update draft - Interpret and draft results | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Thu, Jun 25 | Project Work
Morning:
| Interns Work on Project - Work on advanced models and update draft - Interpret and draft results | 8:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns Work on Project - Work on advanced models and update draft - Interpret and draft results | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Fri, Jun 26 | Project Work
Morning:
| Prepare for progress report | 8:00 AM - 10:00 AM |  | Grad Fellows
| Progress Report (10-15 minute presentation + 5-10 minutes Q&A) | 10:00 AM - 12:00 PM | Hutch 302 | All Teams
Afternoon:
| Interns Work on Project - Work on advanced causal models -update draft of statistics models and results -Incorporate feedback | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Week 5 Deliverables: | A draft of econometric models and preliminary results
A progress report

## Week 6
Week 6: Advanced Skills and Topics
Date | Event/Activities | Time | Location | Responsible Parties
Mon, Jun 29 | AI - Advanced Computing at VT
Morning:
| Grad Fellows and Interns meet with faculty leads to plan for the week - Faculty leads talk about big picture and goals - Grad Fellows meet with individual groups to assign tasks | 8:00 AM - 9:00 AM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Workshop - AI - Advanced Computing - https://arc.vt.edu/services/training.html | 9:00 AM - 12:00 PM | Kohl Centre Hutch 320 | Dr. C Wang schedule "Visualizing this"
Afternoon:
| Interns work on Project - Work on analysis and update draft of results | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Tue, Jun 30 | Large Language Models (Optional)
Morning:
| Workshop - LLM | 1 hr | Kohl Centre Hutch 320 | ???
| Interns work on Project - Work on analysis and update draft of results |  |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Prepare for presentation for stakeholder meeting | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Wed, July 1 | Large Language Models + R (Optional)
Morning:
| Workshop - LLM + R | 1 hr | Kohl Centre Hutch 320 | ???
Interns work on Project - Prepare for presentation for stakeholder meeting
| Interns meet with Stakeholder - potential slots | 10:00 AM - 12:00 PM |  | Project Team and Stakeholder
Afternoon:
| Interns work on Project - Work on analysis and update draft of results | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Interns meet with Stakeholder - potential slots | 1:00 PM - 4:00 PM |  | Project Team and Stakeholder
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Thu, July 2 | Project Work
Morning:
| Prepare for progress report | 8:00 AM - 10:00 AM |  | Grad Fellows
| Progress Report (10-15 minute presentation followed by 5-10 minutes Q&A) | 10:00 AM - 12:00 PM | Hutch 302 | All Teams
Afternoon:
| Interns work on Project - Work on analysis and update draft of results - Incorporate feedback | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Interns meet with Stakeholder - potential slots | 1:00 PM - 4:00 PM |  | Project Team and Stakeholder
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Fri, July 3 | Independence Day Observed - No Activities
Week 6 deliverables: | A complete draft of restuls
Midterm Check In with Stakeholders
A progress report

## Week 7
Week 7: Project Work
Date | Event/Activities | Time | Location | Responsible Parties
Mon, Jul 6 | Poster Creation
Morning:
| Grad Fellows and Interns meet with faculty leads to plan for the week - Faculty leads talk about big picture and goals - Grad Fellows meet with individual groups to assign tasks | 8:00 AM - 9:00 AM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Workshop - Poster and Latex | 9:00 AM - 11:00 AM | Kohl Centre Hutch 320 | Dr. Yujuan Gao
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Tue, Jul 7 | Project Work
Morning:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster | 8:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Wed, Jul 8 | Project Work
Morning:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster | 8:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Thu, Jul 9 | Project Work
Morning:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster | 8:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on Kohl Insights | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Fri, Jul 10 | Project Work
Morning:
| Prepare for progress report | 8:00 AM - 10:00 AM |  | Grad Fellows
| Progress Report (10-15 minute presentation followed by 5-10 minutes Q&A) | 10:00 AM - 12:00 PM | Hutch 302 | All Teams
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on Kohl Insights | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Week 7 deliverables: | A preliminary poster
A revised R-shiny
Started a draft of Kohl Insights
A progress report

## Week 8
Week 8: Project Work
Date | Event/Activities | Time | Location | Responsible Parties
Mon, Jul 13 | Project Work
Morning:
| Grad Fellows and Interns meet with faculty leads to plan for the week - Faculty leads talk about big picture and goals - Grad Fellows meet with individual groups to assign tasks | 8:00 AM - 9:00 AM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 9:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Tue, Jul 14 | Project Work
Morning:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 8:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Wed, Jul 15 | Project Work
Morning:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 8:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Write abstract for VT Undergraduate Research Symposium - Submit abstract to Drs. Cary and Gao for approval and submission | 1:00 PM - 4:00 PM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Thu, Jul 16 | Project Work
Morning:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 8:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Fri, Jul 17 | Project Work
Morning:
| Prepare for progress report | 8:00 AM - 10:00 AM |  | Grad Fellows
| Progress Report (10-15 minute presentation followed by 5-10 minutes Q&A) | 10:00 AM - 12:00 PM | Hutch 302 | All Teams
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Week 8 deliverables: | A close-to-finished poster
A close-to-finished R-shiny
A close-to-finished draft of Kohl Insights
Deploy Version 1 of Shiny App
| Abstracts for VT Undergraduate Research Symposium | Due ???
A progress report

## Week 9
Week 9: Finalize project work
Date | Event/Activities | Time | Location | Responsible Parties
Mon, Jul 20 | Project Work
Morning:
| Grad Fellows and Interns meet with faculty leads to plan for the week - Faculty leads talk about big picture and goals - Grad Fellows meet with individual groups to assign tasks | 8:00 AM - 9:00 AM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 9:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Tue, Jul 21 | Project Work
Morning:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 8:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Wed, Jul 22 | Project Work
Morning:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 8:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Work on analysis and R-shiny app - Work on poster - Work on Kohl Insights | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Thu, Jul 23 | Finish Shiny App + Poster + Kohl Insights
Morning:
| Interns work on Project - Finish analysis and R-shiny app - Finish poster - Finish Kohl Insights | 8:00 AM - 12:00 PM |  | Grad Fellows available for questions
Afternoon:
| Interns work on Project - Finish analysis and R-shiny app - Finish poster - Finish Kohl Insights | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Fri, Jul 24 | Progress Report and Poster Review
Morning:
| Prepare for progress report | 8:00 AM - 10:00 AM |  | Grad Fellows
| Progress Report (10-15 minute presentation followed by 5-10 minutes Q&A) | 10:00 AM - 12:00 PM |  | All Teams
Afternoon:
| Interns work on Project - Poster Review - Practice poster presentation (7-8 minute presentations) - Submit poster for print | 1:00 PM - 4:00 PM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Week 8 deliverables: | A finalized poster
A finalized R-shiny App
A finalized draft of Kohl Insights

## Week 10
Week 10: Summer VT Undergraduate Research Symposium and Publish Projects on Websites
Date | Event/Activities | Time | Location | Responsible Parties
Mon, Jul 27 | Finalize Project Work + Present to stakeholders
Morning:
| Grad Fellows and Interns meet with faculty leads to plan for the week - Faculty leads talk about big picture and goals - Grad Fellows meet with individual groups to assign tasks | 8:00 AM - 9:00 AM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Interns practice stakeholder presentations with Grad Fellows | 9:00 AM - 10:00 AM |  | Grad Fellows
| Interns practice poster presentation with Grad Fellows | 10:00 AM - 11:00 AM |  | Grad Fellows
| Interns mock poster presentation with faculty leads | 11:00 AM - 12:00 PM (7-8 minutes each group) |  | Faculty leads
Afternoon:
| Interns work on Project - Finalize R-shiny app (last minute changes) - Finalize Kohl Insights (last minute changes) | 1:00 PM - 4:00 PM |  | Grad Fellows available for questions
| Interns present final project to Stakeholder - potential slots | 1:00 PM - 4:00 PM |  | Project Team and Stakeholder
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Tue, Jul 28 | Finalize Project Work + Present to stakeholders
Morning:
| Interns present final project to Stakeholder - potential slots | 8:00 AM - 12:00 PM |  | Project Team and Stakeholder
| Interns finalize project and schedule meetings with faculty leads to get approval | 10:00 AM - 12:00 PM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
Afternoon:
| Interns finalize project and schedule meetings with faculty leads to get approval | 1:00 PM - 4:00 PM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
| Interns present final project to Stakeholder - potential slots | 1:00 PM - 4:00 PM |  | Project Team and Stakeholder
| Push progress to GIT, Make sure to follow Template, Reflection | 4:00 PM - 5:00 PM |  | Grad Fellows
Wed, Jul 29 | Publish Projects
Morning:
| Interns finalize project - Publish R-Shiny App - Publish Kohl Insights - Tidy up Github Repo | 8:00 AM - 12:00 PM |  | Drs. Michael Cary and Yujuan Gao, Grad Fellows
Afternoon:
| Practice Presentations with Posters | 1:00 PM - 5:00 PM
Thu, Jul 30 | Summer VT Undergraduate Research Symposium
| Symposium | 8:30 AM - 4:00 PM | Goodwin Hall Atrium | All Teams
| After Party | 17:30 | TBD | All Teams
Fri, Jul 31 | Wrap-up
Morning:
| Fill out Exit Survey on laptop | 8:30 AM - 9:30 AM |  | Dr. Michael Cary
| Tidy office to its original state | 9:30 AM - 9:45 AM
| Return all laptops | 9:40 AM - 10:00 AM |  | Dr. Michael Cary
| Update CV | 10:00 AM - 11:30 AM |  | Dr. Michael Cary
| Return keys to Normand Adams | 11:30
| Interns check out of dorm - check Teams for dorm move out instructions | 12:00 PM - 12:30 PM
Week 10 deliverables: | Kohl Insights
R-Shiny App
Github Repo
Stakeholder Presentation
Poster Presentation at Symposium